## Security Findings
ID | Severity | Category | Title | Description | Phase | Status
F-01 | CRITICAL | Secret Exposure | API Key Exposed in Git History | Third-party API key committed to git. Key revoked, .env removed from tracking. | Phase 2 | Done
F-02 | HIGH | Secret Exposure | Email Credentials in .env.example | Real Gmail address and app password in example env file. Credentials revoked. | Phase 2 | Done
F-03 | HIGH | Cryptography | API Key in URL Query Parameter | Gemini API key passed as ?key= URL param. Moved to x-goog-api-key header. | Phase 2 | Done
F-04 | HIGH | SSRF | Webhook URL Validation Missing | Webhook endpoint accepted internal network addresses. Added SSRF protection. | Phase 2 | Done
F-05 | HIGH | XSS | Stored XSS via Email Templates | User variables not escaped in HTML email bodies. Applied html.escape(). | Phase 2 | Done
F-06 | HIGH | Authentication | Missing Secure Flag on Cookies | Session/CSRF cookies lacked Secure flag. Added Secure=True in production. | Phase 2 | Done
F-07 | MEDIUM | Authentication | No Rate Limiting on MFA Endpoint | MFA verify had no rate limiting allowing brute-force. Extended rate limiter. | Phase 3 | Done
F-08 | MEDIUM | Credentials | Hardcoded Seed Passwords | Seed script set identical passwords. Replaced with random + must_change_password. | Phase 3 | Done
F-09 | MEDIUM | Cryptography | PostgreSQL Without TLS | No TLS on DB connection. Added PGSSLMODE=require via systemd override. | Phase 3 | Done
F-10 | MEDIUM | Audit Trail | Failed Logins Not Logged | Auth failures not in audit log. Added log_audit() with IP and username. | Phase 4 | Done
F-11 | MEDIUM | Audit Trail | Deletion Events Missing Identifiers | Deletion audit logs had only numeric IDs. Added key_prefix and URL lookup. | Phase 4 | Done
F-12 | MEDIUM | Logic | Email Password Sentinel Collision | Bullet char sentinel could match real password. Replaced with '__unchanged__'. | Phase 4 | Done
F-13 | MEDIUM | Data Integrity | Bulk Import Partial Commit | Per-row inserts left partial data on failure. Rewritten with atomic transaction. | Phase 4 | Done
F-14 | LOW | Security Headers | Missing COOP and CORP Headers | COOP and CORP headers absent. Both added to security headers middleware. | Phase 5 | Done
F-15 | LOW | Security Headers | CSP Allows External Font CDN | CSP permitted external font sources. Fonts already self-hosted. Restricted. | Phase 5 | Done
F-16 | LOW | Dependencies | Three CVEs in Dependencies | jinja2, python-multipart, python-dotenv had CVEs. All upgraded. | Phase 6 | Done
F-17 | HIGH | Authorization | IDOR on Task and Calendar Endpoints | Task update, delete, and calendar CRUD lacked ownership checks. Any authenticated user could modify another user's items by guessing IDs. Added created_by/assigned_to validation on all mutating endpoints. | Phase 6 | Done
F-18 | HIGH | Input Validation | No Input Sanitization | All 89+ JSON endpoints and 20+ Form endpoints accepted raw HTML/script tags. Added centralized core/sanitize.py with sanitize_dict() for JSON bodies and sanitize_str() for Form params. Rich text fields (policy content, HTML bodies) bypass tag stripping. Passwords exempt. | Phase 6 | Done
F-19 | HIGH | Access Control | No CORS Origin Blocking | Backend accepted requests from any Origin header. External domains could make cross-origin requests to the API. Added cors_block_middleware that rejects requests with non-whitelisted Origin headers. | Phase 6 | Done
F-20 | MEDIUM | Information Disclosure | Verbose Error Pages Expose Stack Traces | Unhandled exceptions returned raw Python tracebacks to the browser, allowing attackers to map internal paths, libraries, and versions. Added generic branded error page for 403, 404, and 500 responses. | Phase 6 | Done
F-21 | MEDIUM | DoS | No Request Body Size Limit | No limit on request body size allowed attackers to send arbitrarily large payloads to exhaust server memory. Added body_size_limit_middleware rejecting requests over 5MB with 413 status. | Phase 6 | Done
F-22 | MEDIUM | Information Disclosure | Readiness Probe Leaks Exception Details |  | Phase 6 | Done
F-23 | LOW | Performance | Missing Database Indexes on High-Traffic Queries | 17 frequently queried columns (status, user_id, created_by, expires_at, etc.) across 10+ tables had no indexes, causing full table scans under load. Added indexes to all high-traffic query fields. | Phase 6 | Done
F-24 | HIGH | Access Control | No Row Level Security on Shared Tables | Public schema tables (users, audit_log, licenses) had no RLS policies. A search_path misconfiguration could leak cross-org data. Added FORCE ROW LEVEL SECURITY with tenant_isolation policies gated on app.current_org_id, app.is_super_admin, and app.bypass_rls session variables. Auth layer uses bypass connections. Policies applied idempotently at startup. | Phase 6 | Done
F-25 | MEDIUM | Cryptography | API Key Hash Upgraded to PBKDF2 | API key hashing upgraded from HMAC-SHA256 to PBKDF2-SHA256, 100k iterations (commit 3ad2671). Old HMAC-format keys will not validate - confirm regeneration happened. | Phase 9 | Done
F-26 | MEDIUM | XSS | Second CodeQL Sweep: DOM XSS Batch | 6 additional DOM XSS fixes post-v1.0.2: documents.html, BCM doc viewer, analytics.html, notification click handler (2 sites), analytics insights panel. | Phase 9 | Done
F-27 | LOW | Path Traversal | Second CodeQL Sweep: Path/Injection Batch | 4 additional path-traversal/injection fixes in report and GRID endpoints, plus a filename regex validation added as defense in depth. | Phase 9 | Done
F-28 | LOW | ReDoS | Tag-Stripping Regex ReDoS | security.py tag-stripping regex replaced with a linear scan. | Phase 9 | Done
F-29 | MEDIUM | Secret Exposure | Clear-Text Secret Storage in .env | App stopped writing secrets to the app .env file; SECRET_KEY logging removed from start_app.py. | Phase 9 | Done
F-30 | LOW | CSRF | Login CSRF Loop | csrf_token cookie was not set on error responses, causing a login CSRF loop. Fixed in commit 0190833. | Phase 9 | Done
F-31 | MEDIUM | Access Control | Audit Log Org Isolation Hardened | Strict filtering added for non-super-admins on the audit log (commit 27f8446), beyond the original PLAN-01 tenant-isolation fix. | Phase 9 | Done
F-32 | LOW | Injection | AI Prompt Injection Protection | Prompt-injection protection and AI-endpoint rate limiting added (commit 4ab948a); all user inputs now sanitized at request boundaries (commit 6d00661). | Phase 9 | Done

## ZAP Scan Results
Warning | Count | Risk | Detail | Disposition
Cache-control on robots.txt [10015] | x1 | LOW | robots.txt lacks cache-control. Nginx serves this directly. | Accepted
X-Content-Type-Options on robots.txt [10021] | x1 | LOW | Header set by FastAPI middleware, not propagated to Nginx static. | Accepted
HSTS Not Set [10035] | x3 -> x1 | MEDIUM | Main domain and sitemap fixed via Cloudflare. robots.txt remains (Nginx). | Remediated
Non-Storable Content [10049] | x3 | LOW | 403 responses lack Cache-Control. 403s should not be cached. | Accepted
CSP No Fallback Directive [10055] | x8 | LOW | worker-src/manifest-src not explicit. default-src 'self' covers per spec. | Accepted
Timestamp Disclosure [10096] | x2 | LOW | Unix timestamps in 403 error responses. Not exploitable. | Accepted
Modern Web Application [10109] | x3 | INFO | Informational: site uses modern JavaScript frameworks. | Informational
CORP Missing on robots.txt [90004] | x1 | LOW | CORP header not propagated to Nginx-served static files. | Accepted

## Pre-Launch Checklist
Category | Item | Details | Owner | Status
Session and Cookie Security
Cookies | Session cookie flags | HttpOnly, SameSite=Strict, Secure, max_age |  | Done
Cookies | CSRF cookie flags | HttpOnly, SameSite, Secure, max_age=3600 |  | Done
Cookies | CSRF via HMAC | Token derived from session via HMAC, no separate cookie needed |  | Done
Cookies | Logout cookie cleanup | delete_cookie with path, samesite, secure flags |  | Done
Cookies | POST-only logout | GET /logout redirects without destroying session |  | Done
Cookies | CSRF origin-check middleware | Blocks cross-origin POST/PUT/DELETE/PATCH |  | Done
Cookies | HSTS header | max-age=63072000, includeSubDomains, preload (prod only) |  | Done
Authentication and Access Control
Auth | bcrypt password hashing | Cost factor 12 |  | Done
Auth | Password complexity | 8+ chars, upper, lower, digit, special |  | Done
Auth | TOTP MFA | RFC 6238, backup codes, pyotp |  | Done
Auth | Session token hashed in DB | SHA-256, prevents token DB dump attacks |  | Done
Auth | Rate limiting | 5 attempts / 5 min for login, MFA, password change |  | Done
Auth | DB-backed rate limiting | PostgreSQL rate_limit_attempts table |  | Done
Auth | Org isolation | Enforced across all admin user management routes |  | Done
Auth | RBAC | Capability-based access control |  | Done
Auth | Licence enforcement | Per-tenant module licensing |  | Done
Infrastructure and Operations
Infra | PostgreSQL migration | Migrated from SQLite to PostgreSQL |  | Done
Infra | PostgreSQL TLS | PGSSLMODE=require via systemd override |  | Done
Infra | Systemd service | Environment isolation via drop-in configuration |  | Done
Infra | Nginx reverse proxy | Port 8080, HTTPS termination via Cloudflare |  | Done
Infra | Database backups | pg_dump at 2 AM daily, 7-day retention, /project/backup_db.sh |  | Done
Infra | Static asset caching | 1 year max-age, immutable for /static/ |  | Done
Infra | Log rotation | Configure logrotate for app and backup logs |  | Done
Infra | Uptime monitoring | External ping service (UptimeRobot or similar) |  | Done
Infra | Email delivery | Verify SMTP credentials and test full flow |  | Done
Infra | Nginx rate limiting | Add rate limiting at reverse proxy level |  | Done
Infra | Firewall rules | Verify only ports 80, 443 exposed |  | Done
Cloudflare Coverage
Cloudflare | SSL/TLS termination | Full Strict mode |  | Done
Cloudflare | DDoS mitigation | Automatic, always-on |  | Done
Cloudflare | HSTS enforcement | 6 months, includeSubDomains |  | Done
Cloudflare | CDN caching | Static asset caching at edge |  | Done
Cloudflare | Bot management | Basic bot detection enabled |  | Done
Cloudflare | WAF rules | Review and enable OWASP Core Rule Set |  | N/A - Free plan (Free Managed Ruleset active)
Cloudflare | Page rules | Configure caching for API vs static routes |  | Done
Cloudflare | Edge rate limiting | Rate limiting rules for login/API endpoints |  | Done (nginx layers + CF leaked credential rule)
Monitoring and Analytics
PostHog | JS snippet | Integrated via meta tags in base_shell.html |  | Done
PostHog | User identification | posthog.identify() with ID, email, name, role |  | Done
PostHog | Autocapture | Pageviews, page leaves, clicks |  | Done
PostHog | CSP allowlist | PostHog domains in script-src and connect-src |  | Done
Sentry | DSN configured | SENTRY_DSN in /project/.env on VPS |  | Done
Sentry | SDK integrated | Python Sentry SDK in application |  | Done
Sentry | CSP allowlist | sentry.io domains in connect-src |  | Done
Sentry | Test event verified | Confirmed in Sentry dashboard 19 June 2026 |  | Done
Sentry | Alert rules | Configure notifications for new errors |  | Done
Sentry | Release tracking | Tag deploys with git commit hash |  | Done
Landing Page
Landing | Tailwind CSS compiled | CDN replaced with purged 25KB CSS |  | Done
Landing | Three.js deduplication | Removed eager-loaded duplicate script |  | Done
Landing | WebGL zero-dimension guard | Guard on Spline 3D canvas init |  | Done
Landing | Console errors eliminated | 260+ errors reduced to 0 (6 Spline warnings remain) |  | Done
Landing | Image optimization | Compress hero images, add WebP fallbacks |  | Done
Landing | SEO meta tags | Verify Open Graph, Twitter Card, description |  | Done
Final Deploy Steps
Deploy | Push latest code | Cookie hardening, landing page, security hardening, Sentry bug fixes |  | Done
Deploy | git pull on VPS | Pull latest from master on /project |  | Done
Deploy | Restart service | systemctl restart themisiq-app |  | Done
Deploy | Run test suite | pytest on production after deploy |  | Done
Deploy | Smoke test all modules | Login, navigate each module, verify no 500s |  | Pending
Application Security
App Security | IDOR protection | Ownership checks on task and calendar CRUD endpoints |  | Done
App Security | Input sanitization | core/sanitize.py: sanitize_dict() on all JSON bodies via _json_body() helpers, sanitize_str() on all Form() params. Rich text keys bypass tag stripping. Passwords exempt. |  | Done
App Security | CORS origin blocking | Middleware rejects requests from non-whitelisted Origin headers |  | Done
App Security | Generic error pages | Branded error page for 403, 404, 500 to prevent vulnerability mapping |  | Done
App Security | Request body size limit | 5MB body size limit middleware to prevent DoS via large payloads |  | Done
App Security | Database query indexes | 17 indexes added on high-traffic query columns across 10+ tables |  | Done
App Security | PG type mismatch fixes | Fixed 3 Sentry crashes from TEXT vs date/timestamp comparisons in PG |  | Done
App Security | Row Level Security | PostgreSQL RLS on public.users, public.audit_log, public.licenses. Policies enforce org_id matching via session variables. Auth and provisioning use bypass connections. Applied idempotently at startup. |  | Done

## Post-Launch
Priority | Item | Details | Status
P1 | Authenticated ZAP scan | Run ZAP with valid session credentials for deeper coverage | Pending
P1 | Sentry alert rules | Configure notifications for new production errors | Done
P1 | Uptime monitoring | External ping service with alerting | Done
P2 | API rate limiting | Application-level rate limiting beyond login endpoints | Done
P2 | CSP report-uri | Collect and monitor CSP violation reports | Pending
P2 | Cloudflare WAF rules | Enable OWASP Core Rule Set -- Pre-Launch Checklist sheet says N/A, free plan, Free Managed Ruleset active. Not independently re-verified 2026-08-07; confirm if still accurate. | N/A (see Checklist)
P2 | Log rotation | Configure logrotate for app and backup logs | Done
P3 | Dependency audit automation | Scheduled pip-audit in CI pipeline | Pending
P3 | CI/CD pipeline | Automated test runs on push | Pending
P3 | Log aggregation | Centralized logging with rotation and search | Pending
P3 | DB connection pooling | Review and optimize connection pool settings | Pending
P3 | Backup restoration test | Verify dump can be restored cleanly | Pending
P3 | HSTS preload submission | Submit to preload list after stable HSTS period | Pending
P4 | Quarterly ZAP scans | Scheduled security re-testing | Pending
P4 | SOC 2 / ISO 27001 evidence | Collect audit logs, access control evidence | Pending
P4 | Image optimization | Compress landing page images, add WebP fallbacks (confirmed done 2026-08-07: all images on landing_page/index.html are .webp) | Done

## Bug Fixes
Bug | Module | Root Cause | Fix | Status
GRID dashboard 500 | GRID | PostgreSQL strict GROUP BY | Added MAX() wrappers and full GROUP BY column list | Done
PostHog JS syntax error | Platform | Jinja2 auto-escaping in script blocks | Moved PostHog config to meta tags, read from DOM | Done
MFA disabling on setup visit | Auth | start_enrollment called on every GET /mfa/setup | Conditional: only call if not already enrolled | Done
Forced password change CSRF | Auth | CSRF token derived from cookie, not session | HMAC-derived CSRF token bound to session | Done
Org deletion FK violation | Admin | audit_log.org_id and api_keys blocked DROP | Null audit_log.org_id and delete api_keys before DROP | Done
User deletion FK violation | Admin | Multiple FK references to user not cleaned up | Clean all FK-referenced rows before DELETE | Done
New org user CSRF failure | Admin | CSRF cookie not set for forced password change | Session-based CSRF derivation | Done
Mobile sidebar positioning | UI | Module sidebar not beside icon nav on mobile | Fixed CSS positioning for mobile drawer | Done
Starlette TemplateResponse API | Admin | New Starlette requires request as first arg | Updated all TemplateResponse calls | Done
New User modal not opening | Admin | Wrong CSS class name in template | Fixed class name typo | Done
Vault expiry notifications crash | GRID | TEXT column compared to bare CURRENT_DATE on PostgreSQL | Use sql_current_date() which casts to ::text on PG | Done
Evidence expiry alerts crash | GRID | TEXT expires_at compared to bare CURRENT_DATE on PostgreSQL | Use sql_current_date() which casts to ::text on PG | Done
Reminders and dashboard queries crash | Platform | sql_now_offset() missing ::text cast, TEXT < timestamptz fails on PG | Added ::text cast to sql_now_offset() in database.py | Done
HEAD requests returning 405 on /health and /ready | Platform | FastAPI 0.111/Starlette 0.37 stopped auto-handling HEAD on GET-only routes. UptimeRobot uses HEAD by default. | Changed @app.get to @app.api_route with methods=[GET, HEAD] on both endpoints. | Done
ERM dashboard 500 - timestamp type mismatch | ERM | sql_now_offset() returned ::text cast; erm_enterprise_risks.created_at is TIMESTAMPTZ in PG. TIMESTAMPTZ < TEXT fails. | Added sql_now_ts() and sql_date_ts() without ::text cast for TIMESTAMPTZ columns. Fixed 5 query sites across ERM, ORM, launcher, predictive_risk. | Done
Test suite hitting live PostgreSQL DB | Tests | DATABASE_URL set in VPS env made settings.is_postgres() return True at import time, bypassing the _DB_PATH monkeypatch. All 72 tests ran against production DB with no isolation. | Set os.environ["DATABASE_URL"] = "" in conftest before any project import. Now forces SQLite mode with fresh isolated DB per test. | Done
RoPA AI risk score never persisted | Sentinel | api_ai_score_ropa built update_data with key "risk_score", but the _ROPA_FIELDS whitelist in data_service.py only allows "risk_level" - _generic_update() silently drops unknown keys | Changed the dict key to "risk_level" so AI risk scoring actually updates the risk badge (ai_risk_notes and dpia_required were already saving correctly) | Done
Gemini API key leaked into logged URLs | ARIA / Sentinel | modules/aria/ai_generator.py and modules/sentinel/ai_service.py each had their own Gemini call building the URL as ...generateContent?key={key} instead of passing it via header | Migrated both modules onto core.ai_client, which already passes the Gemini key via x-goog-api-key header (guarded by an existing regression test, test_gemini_key_in_header_not_url) | Done
SQL comment semicolons broke PG startup | Platform | Semicolons inside SQL comments were parsed as statement terminators by PostgreSQL executescript | Rewrote affected comments; hit and fixed twice (76b04e5, a5d44d1) | Done
workflow_actions missing PG columns | Workflow | due_at/acted_at columns existed in SQLite schema but not in the PostgreSQL migration path | Added missing column migrations | Done
sentinel_breaches missing PG columns | Sentinel | Production breach creation failed due to missing columns on PostgreSQL | Added missing column migrations | Done
Tenant provisioning FK ordering hazard | Platform | applications.vendor_id referenced canonical_vendors, a table created later in the same provisioning script | Reordered table creation; hit and fixed twice (9103e45, 6daa517) | Done
Predictive risk: Sentinel signal always zero | ERM | Breach telemetry was not wired into the 6-signal predictive risk model | Fixed signal wiring; separately fixed again for PostgreSQL (c362a36) | Done
First-login-of-the-day 429 | Auth | Rate limiter incorrectly flagged the first login attempt of a new day | Fixed rate-limit window logic (b4ee3fa) | Done
NameError crashes on startup and dashboards | Platform | _logging undefined in database.py; role-detection NameErrors in Command Centre stats and My Dashboard | Fixed undefined references (4e56802, ce43a81) | Done
GRID audit-log gap: 15 mutation endpoints | GRID | 15 mutation routes (evidence, comments, reminders, mappings, timeline, remote sessions) never called log_activity() | Added log_activity() calls at all 15 sites, live-verified via DB | Done
ORM RCSA Controls/Actions had no frontend | ORM | Backend routes existed for RCSA control and action sub-entities but no UI ever called them | Built full nested Controls/Actions CRUD in the RCSA drawer | Done
ARIA compliance stats read wrong/empty table | ARIA | 5 sites (dashboard, platform stats, predictive risk, evidence AI-link suggestions) read aria_controls, an unused legacy table, instead of the live controls table | Redirected all 5 sites to the correct table; dropped the one genuinely dead table (aria_evidence) after re-verifying aria_frameworks/aria_controls were still load-bearing | Done
Sentinel: 7 sub-page field mismatches | Sentinel | Security Measures, Retention, Transfers, Policies, Vendors, Consent, and Notices sub-pages had frontend/backend field name mismatches | Fixed all 7 field mismatches plus a Reports page early-return bug | Done
BCM: risk-creation crash + 4 dead fields | BCM | Risk creation crashed under certain inputs; 4 sub-page fields were captured in the UI but never persisted | Fixed crash and wired all 4 fields end to end | Done

## AI Guardrails
Module | AI Feature | Guardrail(s) Applied | Human Review Required? | Notes / Status
ARIA | Policy / Document Generation | GRC guardrail (domain-restricted, anti-hallucination, cites law) via core.ai_client; prompt-injection wrapping (<user_input> tags); optional user guidance dialog | Yes | Fixed this pass: was bypassing core.ai_client entirely (no guardrail, Gemini key in URL). Saved as Draft status with an explicit disclaimer requiring formal approval before use.
ARIA | Gap Analysis | GRC guardrail via core.ai_client | No | Fixed this pass (same bypass as above). Shown for review, not auto-persisted.
ARIA | Ask ARIA (Q&A over corpus) | GRC guardrail via core.ai_client; answers grounded only in retrieved document chunks; declines and suggests nearest owner if no chunk covers the question | No | Migrated onto core.ai_client this pass. Answer shown directly with source citations.
ARIA | Auto Control Mapping (IMS) | GRC guardrail via core.ai_client; 3-pass hybrid (category grouping, text similarity, AI only for ambiguous 0.35-0.65 score pairs) | Partial | Confidence score and match method shown; user reviews generated mappings.
Sentinel | DPIA Research | GRC guardrail via core.ai_client; optional user guidance dialog; prompt-injection wrapping | No | Fixed this pass: was bypassing core.ai_client. Shown for review before saving.
Sentinel | Full DPIA Generation | GRC guardrail via core.ai_client; optional user guidance dialog | No | Auto-saved to ai_full_dpia. See Known Gap row below - not changed this pass.
Sentinel | RoPA Risk Scoring + DPIA flag | GRC guardrail via core.ai_client; JSON-only output; now auto-triggered on record creation for faster DPIA-required detection | No | Bug fixed this pass: risk_score/risk_level key mismatch meant the AI risk level was never actually saved before now (see Bug Fixes sheet).
Sentinel | Legal Basis Suggestion (new) | Constrained choice: model must copy one option verbatim from the regulation's own pre-approved LEGAL_BASES list; server-side exact/normalised match verifies the result before it is returned - cannot be a hallucinated value | Yes | New this pass. Explicit Apply / Dismiss buttons - never auto-applied to the form.
Sentinel | Breach Impact Assessment | GRC guardrail via core.ai_client | No | Auto-saved to ai_assessment. See Known Gap row below.
Sentinel | DSR Draft Response | GRC guardrail via core.ai_client | No | Auto-saved to ai_draft and used as a legal response letter. See Known Gap row below.
Sentinel | Privacy Notice Generation | GRC guardrail via core.ai_client | No | Shown for review, not auto-persisted.
Sentinel | Vendor / Processor Check | GRC guardrail via core.ai_client | No | Auto-saved to ai_assessment. See Known Gap row below.
Sentinel | Privacy Compliance Chat | GRC guardrail via core.ai_client; multi-turn history now passed correctly for every provider | No | Fixed this pass: openai/gemini providers previously fell back to single-turn calls and silently dropped conversation history.
Sentinel | Cross-Regulation Gap Analysis | GRC guardrail via core.ai_client | No | Shown for review, not auto-persisted.
GRID | Risk scoring, checklist parsing, gap analysis, control suggestion, report narrative, compliance chat | GRC guardrail via core.ai_client (already integrated before this pass) | Mixed | Not touched this pass - already routes through the shared guardrailed client.
ERM | Risk scoring, treatment suggestion, board narrative, chat, risk statement, assessment questions, remediation plan | GRC guardrail via core.ai_client (already integrated before this pass) | Mixed | Not touched this pass. Risk scoring auto-persists likelihood/impact/category/treatment.
ORM | Event root cause analysis, board report, chat | GRC guardrail via core.ai_client (already integrated before this pass) | Mixed | Not touched this pass. Root cause analysis auto-persists; others are reviewed first.
BCM | Plan review, incident actions, RAG Q&A, plan generation, chat, board narrative | GRC guardrail via core.ai_client (already integrated before this pass) | Yes | Not touched this pass. All features are reviewed before persistence.
Evidence | Auto-Suggest Links | GRC guardrail via core.ai_client | Yes | Not touched this pass. User confirms suggested links before they are created.
Launcher | Task prioritisation, executive summary, THEMIS help bot | GRC guardrail via core.ai_client | Yes | Not touched this pass. Suggestions are applied manually by the user.
Cross-cutting | Rate limiting | 60 AI requests / hour per user (check_ai_rate_limit / record_ai_call), returns 429 when exceeded | N/A | Applies to Sentinel, ARIA, ERM, ORM, and BCM AI endpoints.
Cross-cutting | Prompt injection defence | wrap_user_input() / _u() wraps every field sourced from user input (form fields, free text, chat messages) in <user_input> tags before it reaches a prompt | N/A | Consistent pattern across all AI-calling modules.
Cross-cutting | Domain restriction + anti-hallucination | _GRC_GUARDRAIL is prepended to every core.ai_client.create_message() call: restricts scope to GRC topics, requires citing only verifiable named standards/articles, requires saying so when uncertain rather than inventing a citation, refuses role-override / instruction-injection attempts | N/A | Now applied to ARIA and Sentinel too - both previously bypassed this guardrail entirely by calling AI providers directly instead of through core.ai_client.
Known gap | Auto-persist without review | Breach assessments, DSR drafts, full DPIA generation, and ERM/ORM risk scoring all auto-save AI output directly into records used for regulatory, legal, or board-level decisions, with no explicit human sign-off step before the value goes live | Recommended, not fixed | Intentionally out of scope this pass - adding a review-gate is a larger behavioural change spanning several modules than what was requested. Flagged here for a dedicated follow-up.

## Feature Development
Feature | Module | Description | Status
Governance Graph Tier 1 | Governance | 5 new node-type tables (business units, departments, processes, applications, data assets), unified canonical controls model, Control Effectiveness Engine, Residual Risk Engine (ERM and ORM now converge on one formula), Governance Timeline, Ctrl+K command palette, Regulatory Inbox with drift detection, daily advisory briefing. | Done
ERM Risk Rating Framework | ERM | Configurable rating engine (seeded with an OmniContact-derived default), framework editor with clone/import/export so other orgs can bring their own, taxonomy-driven categories, multi-dimension impact scoring, CF/ICE scoring engine, assessment workspace, per-CF treatments, dashboard v2, objectives, AI-assisted external-context/emerging-risk scanning. | Done
Excel Risk Register Import | ERM | Two-phase preview/commit import flow with fuzzy column, category, and owner matching; no data from the source spreadsheet is discarded. | Done
Evidence Vault Rewrite | Platform | Rewritten as a real file repository (was ARIA-fallback only): working download, in-place editing, PDF export, cascade-safe archive/restore/permanent-delete; documents now auto-sync to the vault on upload, not only on approval. | Done
Workflow Engine Overhaul | Platform | Fixed role resolution, auth checks, status handling, and task-delete bugs; added an SLA auto-check scheduler, multi-role steps, auto-trigger, step deadlines, and delegation. Workflow and task-board updates are now concurrency-safe. | Done
WhatsApp Connector | Platform | Added alongside the existing Slack and Teams connectors: signed webhook fan-out, RBAC-scoped delivery. Configured from Admin > Connectors. | Done
Organisation Administrator Role + Business Units | Platform | Tenant-scoped admin role that can manage users within one organisation without full Super Administrator access; business-unit hierarchy with user assignment for multi-SBU organisations. | Done
User Soft-Delete and Bulk Import/Export | Platform | Users can be soft-deleted and restored (history preserved) or permanently deleted by a Super Administrator; bulk user import/export via Excel with preview and per-row validation. | Done
Landing Page Rebuild | Marketing | Full rebuild at landing_page/index.html: dark liquid-glass design, cinematic hero video (Spline removed entirely), module and AI capability cards, feature deep-dive rows. All images WebP; full SEO/Open Graph/Twitter Card meta tags present. | Done
Icon Sidebar Redesign | Platform | Premium theme-aware glassmorphic nav rail: proper light/dark theme response, stronger backdrop blur, module-accent ambient glow, fixed a status-dot/active-pill colour clash. | Done
Econet Organisation Consolidation | Production Ops | PLAN-31: users and org-structure consolidation, business-unit reassignment, oversight roles, SBU rename, applied directly to production for the Econet tenant. Tenant-schema self-heal added for migration drift on startup (PLAN-32). | Done